## 630 Ton Press
Note…. This is the format of the A3 we are currently teaching. It more explicitly uses the concept of hypothesis testing in questions 4 and 5. This one was done by a Production Manager and it was the first one he did. The project, as the effect confirmation shows is progressing nicely, In particular note the clear connectivity between the target condition (Question 2), impediments (question 3), action items (question 4) and expectations (question 5)
A3 Report
<-----------------------------------------------Plan---------------------------------------> |  |  |  |  | <------------------------------------------Do, Check, Act--------------------------------------->
Project Theme | Increase capacity on 630 ton press. |  |  |  | Problem Owner-Team | Dave - Nicole, Mark, Adam, Gene, Djuro, Ben, Dian, Nic, Clint |  |  |  |  | Rev date:
Problem Statement | 630 press has insufficient OEE and staffing to meet current demand. |  | There should be a "thing" a noun, and something wrong with it, a "defect". |  | Coach | Lonnie Wilson |  |  |  |  | 2018-10-30
Background |  | (1)Explain project background and link past to present; explain "the path" to this problem and, (2) Information why this project was chosen, how it fits with Corp/Plant needs. |  |  | 4-What is something we can do, right now, to get closer to the desired condition? (These are the countermeasures) |  | 5-When we do this….what should we expect to happen? (You must address A, B and C below)
The 630 Ton stamping press was purchased in 2016. Since startup in 2017 the press has had low OEE (overall equipment effectiveness) as shown on the attached OEE graph. While OEE has been improving over time, this press should comfortably perform at greater than 75% OEE. | [6 empty] | A-What Will Happen? (What are the benefits of doing this? Or what would happen if we did not? Be specific and metric oriented) | B-How much will we gain? (from this countermeasure alone, be specific) | C- When will it happen so we can go see? | Responsible | % Complete
Due to low OEEs the press is no longer able to keep up with demand while being manned for 2 shifts, |  |  |  |  | 1A-1 Cross train 3 addtl. Ops. to fill in when needed. |  | Run time will increase. Sustain 88 hours every week vs 80. | 8 hrs. x 3,350pcs/hr. x 42% OEE =11,256 pcs/wk | 2018-10-30 | Djuro | 30%
5 days per week. In addition recent capacity requirements of the CCC project has placed additional |  |  |  |  | (One per month of highest qualified )
demands on this press which is not currently able to keep pace with demand.
This failure to meet demand has reached very serious levels (see Capacity Planning graph (In Planning File ) |  |  |  |  | 1A-2-1 Reduce tool C/O time from 2 hr 6 min to 90 min |  | Run time will increase (7 s/u's x 30min=210 min or 3.5hrs/wk) | 3.5 hrs per wk x 42% OEE = 5,000 pieces per week | 2018-11-30 | Nicole | 0%
[5 empty] | 1A-2-2 Reduce coil C/0 time from 14.5 min to 10 min. |  | Run time will increase (21 CC's x 5min=105min or 1.75hrs/wk) | 1.75 hrs per wk x 42% OEE=2,500 pieces per week | 2018-11-09 | Dave | 80%
Note: with these three items OEE should be ~42%...not yet adequate to run off backlog)
[5 empty] | 1B-1 Hire and train to staff a third shift |  | Run time will increase to provide capacity for the CCC latch | 32 hours per week 3,350 x 32 hrs x 51% OEE = 54,672 pieces. | 2019-03-15 | Dian | 0%
[5 empty] | 1B-2 Hire or dedicate a supervisory resource to third shift |  | Ensure documented processes are being followed and necessary resources are being engaged throughout he night. | If we do not do this run time will be reduced during 3rd shift. | 2019-03-15 | Adam | 0%
[5 empty] | 1B-3 Run 3rd shift on the 400 ton press and transfer some work there. |  | Run time will increase to provide capacity for the CCC latch. Increased risk of missed shipments on other stampings that are produced elsewhere in the department. | 32 hours per week x 2,700 pcs./hr. (400T) x 51% OEE =44,064pcs/week | 2018-10-30 | Dave | 100%
1-What is the present condition? (What Where, When, How much, Risk?) |  | Explain the "is/is not" state, use data and graphs |  |  | 1B-2-1 Assign toolmakers to alternate breaks |  | Toolroom press call availability from toolmakers during break times | Run time will increase as tool breakdowns will not have to wait until lunch or break is over. | 2018-10-08 | Mark | 100%
630 ton press is running at 42% OEE at 3350 pc/hr for 80 hrs on average |  |  |  |  | 1B-2-3-Hire toolmakers for 2nd shift |  | Run time may not improve during 2nd shift. Only one toolmaker is available to address the needs of stamping and die cast trim tools. | Run time will increase as tool breakdowns will not have to wait until a toolmaker is available. | 2018-11-30 | Nic | 0%
Demand is averaging 125,000 pcs/weekper week.
Currently the 630 ton press is capable of producing 113,000 pcs/wk |  |  |  |  | 2-A-1 - Break down job into separate skill sets. |  | An organized approach to training as a natural progression to learn the necessary skills in a specific order. | Time to train individuals wll be reduced. | 2018-11-02 | Dave | 75%
Backlog has been building for months and current backlog is 330,000 pcs |  |  |  |  | 2-A-2 - Apply standard work to set-up training |  | Setup personnel and trainers will begin to follow a disciplined and safe approach to performing the changeover. Training will be more effective. | Consistency in setups will reduce variability from setup to setup. | 2018-12-15 | Djuro | 25%
Our current ability to staff the machine is approximately only 80 hrs.
Demand for the CCC project will consume 31 hours per week of capacity (at 42% OEE) starting early October |  |  |  |  | 3- Clean up standard work developed during Kaizen and implement it into every setup |  | Reduce setup time by 15 minutes x 7 setups/wk. Note: must have cross training in place step 1A-1 above. | 1.75 hrs per wk x 42% OEE=2,500 pieces per week | 2018-11-30 | Dave | 50%
Weekly schedule has frequent changes
[5 empty] | 4- Deliver 2 week firm schedule that includes sampling. |  | Allow consistent pre-staged setups and reduce setup time in 1A-2-1 above. | We will be able to consistently apply our standard work to every setup and ensure optimum setup times. | 2018-12-15 | Barry | 0%
Since 7/1/18 we had 86 changeovers (7/wk) and 270 coil changes (21/wk)
During the months of March thru June we averaged 81.5 hrs/week coverage |  |  |  |  | 5A-1 Review of daily production and OEE at shift change. |  | Increase awareness of daily wins or losses with the team | Results will be longer term-drive problem solving | 2018-10-01 | Mark | 100%
[5 empty] | 5A-2 Update hour by hour boards to use as schedule. |  | Increase operator and supervisor focus on houly production. | Results will be longer term&drive problem solving. | 2018-10-15 | Dave | 100%
[5 empty] | 5B-1 Assign direct maintenance support to the 630 and 400 presses |  | Runtime will increase from reduced response time from maintance resources. | If we do not do this downtime may not be reduced. | 2018-11-15 | Clint | 0%
[5 empty] | 5B-2 Verify all critical spare parts are in place for all equipment on press line. |  | Time lost from not having or wasting time looking for perishable spare parts will be a non-issue | If we do not do this downtime may not be reduced. | 2018-12-15 | Clint | 0%
2-What is the desired future condition? |  | Explain the "desired" state include both results and means (the target condition) |  |  | Effect Confirmation (simple verbal explanation) |  | Effect Confirmation - Graphic (Place a simple graph(s) that will show progress to date. Must comply with "scoreboard effect")
1-Meet the current demand, satisfy the CCC requirements and run off the backlog in 25 weeks |  |  |  |  | Must improve OEE to 50%
1-A We can meet current demand by Oct 15
1-B We can also fully meet CCC requirements by Oct 29 |  |  |  |  | Must improve production:
1-C We can begin runoff of backlog by Mar 15 |  |  |  |  | A- 125,000 pcs per week normal production
1-D Backlog is less than one week by Sept 15 |  |  |  |  | B- 26,000 pcs/ week CCC
(Get the correct numbers) |  |  |  |  | C- 13,000 per week to run off backlog
2-We have a documented training plan in place
3-Standard work for all operations are completed |  |  |  |  | Must run 120 hours per week
4-Two week frozen production schedule
5-A sense of urgency that this press is a top priority
3-What is preventing us from reaching the desired condition? |  | These are the impediments |  |  | 6) What have we learned?
1A-1 We cannot staff for a full 88 hours, mostly due to vacations
1A-2 Current OEE of 42% is inadequate
1B-1 We are not staffed for more than 88 hours
1B-2 Inadequate OEE
1C-completion of all items of 1A and 1B above and OEE must be 50% min.
1D-Must run for 6 months at 120 hours and 50% OEE
2 - Existing training plan needs to be updated.
3 - Hasn't been a high enough priority.
4 - Comittment between SMO and MKE to develop and adhere to a 2 week plan.
5 - Not doing enough to create a high enough sense of urgency.
OEE
Hrs Needed to Meet Demand

## Production - 630T
Date | Production Goal | Actual Production | Hours Staffed | Goal Hrs.
2018-09-17 | 113000 | 263014 | 88 | 88
2018-09-24 | 113000 | 151532 | 94 | 88
2018-10-01 | 130000 | 115883 | 99 | 88
2018-10-08 | 130000 | 100668 | 93 | 88
2018-10-15 | 130000 | 149618 | 102.5 | 88
2018-10-22 | 130000 | 203755 | 91 | 88
2018-10-29 | 139000 |  |  | 88
2018-11-05 | 139000 |  |  | 88
2018-11-12 | 139000 |  |  | 88
2018-11-19 | 139000 |  |  | 88
2018-11-26 | 139000 |  |  | 88
2018-12-03 | 139000 |  |  | 88
2018-12-10 | 139000 |  |  | 88
2018-12-17 | 139000 |  |  | 88
2018-12-24 | 83400 |  |  | 54
2018-12-31 | 83400 |  |  | 54
2019-01-07 | 139000 |  |  | 88
2019-01-14 | 139000 |  |  | 88
2019-01-21 | 139000 |  |  | 88
2019-01-28 | 139000 |  |  | 88
2019-02-04 | 139000 |  |  | 88
2019-02-11 | 139000 |  |  | 88
2019-02-18 | 139000 |  |  | 88
2019-02-25 | 139000 |  |  | 88
2019-03-04 | 139000 |  |  | 88
2019-03-11 | 139000 |  |  | 88
2019-03-18 | 194000 |  |  | 120
2019-03-25 | 194000 |  |  | 120
2019-04-01 | 194000 |  |  | 120
2019-04-08 | 194000 |  |  | 120

## OEE 630T
Month | OEE Goal | Actual OEE
July | 42% | 34%
Aug | 43.45% | 45% | 12 month Improvement | 59.4%
Sept | 44.9% | 47% | Monthly Increment | 1.45%
Oct | 46.35% | 51.9%
Nov | 47.8%
Dec | 49.25%
Jan | 50.7%
Feb | 52.15%
Mar | 53.6%
Apr | 55.05%
May | 56.5%
Jun | 57.95%

## Coil Change Time 630T
Week | Time/Min. Goal | Time/Min. Actual
Baseline | 10 | 14.5
2018-10-08 | 10 | 8.5
2018-10-15 | 10 | 10.75
2018-10-22 | 10 | 8
2018-10-29 | 10
2018-11-05 | 10
2018-11-12 | 10
2018-11-19 | 10
2018-11-26 | 10
2018-12-03 | 10
2018-12-10 | 10
2018-12-17 | 10
2018-12-24 | 10
2018-12-31 | 10
2019-01-07 | 10
2019-01-14 | 10
2019-01-21 | 10
2019-01-28 | 10
2019-02-04 | 10
2019-02-11 | 10
2019-02-18 | 10
2019-02-25 | 10
2019-03-04 | 10
2019-03-11 | 10
2019-03-18 | 10
2019-03-25 | 10
2019-04-01 | 10
Formulas:
Week = [Week, row above]+7

## Tumbler A3 Form (hidden)
A3 Tumbler Report
<-----------------------------------------------Plan---------------------------------------> | [5 empty] | <------------------------------------------Do, Check, Act--------------------------------------->
Project Theme |  | Improve tumbler production performance |  |  |  | Problem Owner-Team |  | Dave Schaefer - Chris Dudzik
Problem Statement |  | Tumblers are causing downtime, expedited freight, and supply issues in SMO |  |  |  | Coach |  | Lonnie Wilson / Adam Gerstmeier | [5 empty] | 2018-05-15
Background |  |  | Information why this project was chosen, how it fits with Corp/Plant needs |  |  | Countermeasures/Implementation Plan |  |  |  | Must address impediments to Target, what will we do now |  |  |  |  | Current Condition: What Where, When, How much | Is/Is Not
In the last 10 months we have had 62 different part numbers totaling 142 instances on the hotlist causing downtime, expedites and resource allocation isses within SMO | [5 empty] | Improvement Activity | [5 empty] | Responsible Teammate | Due Date | % Complete
1) Lack of trained personnel in this area (26 hours / week of "No Operator")
[6 empty] | 1a)Establish training method to measure progress | [5 empty] | Dave Schaefer | 2018-06-18 | 25%
[6 empty] | 1b)Training Ryan and Mike. What is the training plan, how far are we, when do we expect to be complete | [5 empty] | Dave S | TBD
2) Tooling changeover times are lengthy (About 26 hours / week of "set up")
[6 empty] | Create a time sheet to identify time for each step | [5 empty] | Chris / Dave | Complete | 100%
[6 empty] | Collect data on time sheets: Start on 5/25 | [5 empty] | Jim Kurth, Bryant | 2018-06-15 | 0%
[6 empty] | SMED Analysis on the set up | [5 empty] | Chris Dudzik | 2018-06-15 | 0%
[6 empty] | 5S Set up and coil change (Getting Shadow boards for tools on these machines) | [5 empty] | Chris Dudzik | 2018-06-15 | 5%
[6 empty] | Staging of coil and dies for changeovers | [5 empty] | Chris Dudzik | 2018-06-15 | 50%
Current Condition: What Where, When, How much |  |  | Explain the "is" state, use data and graphs |  |  | 3) Lack of tool room die personnel/ Tool repair time is speculated to be high (need data)
We cannot meet current tumbler demand with the way we operate today.We have an average of 9 tumblers on the hot list per week
[6 empty] | Ask Gene why there is a tumbler inbalance (over produce some parts, under produce others) 25 Million on hand and usage of 3.5 Million per week and we are short. (Still researching how the tumbler list is created, however, a lot of the excess inventory in this question is likely caused by family tools. There are hot jobs we are running that have a tool that makes 4 part numbers, and we don't need any of the other 3 parts so it is building inventory) Collect Data on Family tool on high inv parts vs parts on hot list. Need all family tools | [5 empty] | Chris Dudzik | 2018-06-06
[6 empty] | Get a kitting position approved. This could improve 5 hours out of the 15 total time. Will discuss with Adam on his return. | [5 empty] | Adam G. | 2018-09-17 | 0%
[6 empty] | Sending tools to Ultra (outside) | [5 empty] | Dave S. | In Progress
5)Drop-ins on schedule
[6 empty] | Setting up a Kan-ban for 4201932-39 series: 960K | [5 empty] | Dave S.
[7 empty] | -1935 | [5 empty] | Complete | 100%
[7 empty] | -1936 | [5 empty] | complete | 100%
[7 empty] | -1938 | [5 empty] | 2018-06-08 | 5%
6) Monitor Down Time
[6 empty] | Measure Performance: | [5 empty] | Jim O | Continuous | 100%
[6 empty] | Graph Downtime Reasons | [5 empty] | Chris D | Continuous | 100%
[6 empty] | Display performance | [5 empty] | Jim O | 2018-06-01 | 50
Target Condition |  |  | Explain the "desired" state include both results and means |  |  | Effect Confirmation
Goal is reduce tumblers on the hotlist to 5 by 03JUL18. The Ideal goal is to be to 0. The target date for this will be established on July 3rd..
Impediments to Target Condition |  |  | Answer to question 3, what's preventing us from attaining "desired state" |  |  | Follow up Actions
1) Lack of trained personnel in this area
2) Tooling changeover times are lengthy
3) Lack of tool room and die personnel
4) Tool repair time is speculated to be high (need data)
5)Drop-ins on schedule (need data)
6) Identify and Monitor Down Time
Questions to answer at each meeting (standard for each meeting)
| 1 | Since the last meeting, what was I supposed to accomplish
| 2 | What did I learn from that |  |  |  |  | Graph Data
| 3 | What do I plan to accomplish between now and the next meeting |  |  |  |  | Date | Uptime | Schd. Attain | Tmbl HL | OT
| 4 | What problems do I need help on to accomplish that? |  |  |  |  | Baseline | 44% | 35% | 9
[7 empty] | 2018-04-16 | 61% | 87.5% | 13
| 6 Questions of Continuous Improvement | [5 empty] | 2018-04-23 | 46% | 72.1% | 8
| 1 | What is the present Condition? |  |  |  |  | 2018-04-30 | 48% | 92.5% | 7
| 2 | What is the desired future condition? |  |  |  |  | 2018-05-07 | 48% | 90.8% | 8
| 3 | What is preventing us from reaching the desired condition? |  |  |  |  | 2018-05-14 | 77% | 88.4% | 7
| 4 | What is something we can do, right now, to get closer to the desired condition? (Hypothesis test) |  |  |  |  | 2018-05-21 | 73% | 98.6% | 7
| 5 | When we do this, what should we expect? |  | On effect confirmation, the graph should have expecation vs actual |  |  | 2018-05-28 | 75% | 77.1% | 6
|  | A) What will Happen? |  |  |  |  | 2018-06-04
|  | B) What will we gain? How much benefit will we get if this is the issue? If this thing is going to cost a million dollars, would it be worth it? |  |  |  |  | 2018-06-11
|  | C) When will it happen so we can "go see?" |  |  |  |  | 2018-06-18
| 6 | What have we learned? |  |  |  |  | 2018-06-25
2018-07-02
2018-07-09